## Sheet1
Category | Task | Responsible | Start Date | Completion Date
Research | Research artificial intelligence models to determine which model should be used for the application. | Forrest | 2023-10-01 | 2023-11-01
Research | Research database models to determine which model should be used for the application. | Evan | 2023-10-01 | 2023-11-01
Research | Research other workout-focused applications' user interfaces to determine what elements work well and elements do not work well. | JP | 2023-10-01 | 2023-11-01
Design | Design the artificial intelligence that will be used for the application. | Forrest | 2023-11-01 | 2024-01-01
Design | Design the database model that will be used for the application. | Evan | 2023-11-01 | 2024-01-01
Design | Design a user interface based on the research done on other applications. | JP | 2023-11-01 | 2024-01-01
Refine | Refine the artificial intelligence model for determining workout information. | Forrest | 2024-01-01 | 2024-02-01
Refine | Refine the database model for storing workout information. | Evan | 2024-01-01 | 2024-02-01
Refine | Refine the user interface to a completed design. | JP | 2024-01-01 | 2024-02-01
Develop | Develop artificial intelligence for determining workout information from the refined design. | Forrest | 2024-02-01 | 2024-03-01
Develop | Develop the database for storing workout information from the refined database model. | Evan | 2024-02-01 | 2024-03-01
Develop | Develop the user interface based on the refined design. | JP | 2024-02-01 | 2024-03-01
Test | Test the artificial intelligence to ensure the information collected is correct and no bugs are present. | Forrest | 2024-03-01 | 2024-04-01
Test | Test the database to ensure the information is stored correctly and no bugs are present. | Evan | 2024-03-01 | 2024-04-01
Test | Test the developed user interface to ensure usability and no bugs are present. | JP | 2024-03-01 | 2024-04-01